## Gantt Chart
Project Name : Some Example Project |  |  |  |  | Start Date | 2025-06-01
[5 empty] | End Date | 2025-08-31 | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Workstream | Task | Assignee | Start | End | # Days | Progress | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Infra | Set up cloud servers | Alan | 2025-06-01 | 2025-06-05 | 5 | 100
Infra | Configure network firewall | Bryan | 2025-06-06 | 2025-06-08 | 3 | 80
Frontend | Design landing page | Christie | 2025-06-09 | 2025-06-15 | 7 | 60
Frontend | Implement user dashboard | Christie | 2025-06-16 | 2025-06-23 | 8 | 40
Backend | API development | Dan | 2025-06-09 | 2025-06-25 | 17 | 30
Backend | Database schema setup | Alan | 2025-06-05 | 2025-06-10 | 6 | 100
Functional | Requirements gathering | Erica | 2025-06-01 | 2025-06-04 | 4 | 100
Functional | User acceptance criteria | Erica | 2025-06-11 | 2025-06-13 | 3 | 70
QA | Write test cases | Erica | 2025-06-18 | 2025-06-24 | 7 | 0
QA | Functional testing | Erica | 2025-06-25 | 2025-06-30 | 6 | 20
DevOps | Set up CI/CD pipeline | Franco | 2025-06-12 | 2025-06-16 | 5 | 60
DevOps | Deployment to staging | Franco | 2025-07-01 | 2025-07-03 | 3 | 0

## Data Validation
Workstream | Infra | Assignee | Alan
→ | Frontend | → | Bryan
| Backend |  | Christie
| Functional |  | Dan
| QA |  | Erica
| DevOps |  | Franco